## Slide 1: UNIT#2 ACTIVITY PLANNING & SCHEDULING

## Slide 2
Activity Planning
  Means for evaluating the consequences of not meeting any of the activity target dates
  Guidance as to how the plan might most effectively be modified to bring the project back to target
Objectives of Activity Planning
  Feasibility Assessment
  Resource Allocation
  Detailed Costing
  Motivation
  Co-ordination

## Slide 3
Project Schedule
  Before work commences on a project, the project plan must be developed to the level of showing dates when each activity should start and finish and when and how much of each resource will be required
Project Schedule Comprises of 4 Stages
  Creating an Activity Plan
  Activity Risk Analysis
  Resource Allocation
  Schedule Production

## Slide 4
Project and Activities: Defining Activities
  A project if composed of number of inter-related activities
  A project may start when at least one of its activities is ready to start
  A project will be completed when all of its activities it encompasses have been completed
  An activity must have a clearly defined start and end point marked by the production of tangible deliverable
  The duration of an activity must be forecastable
  Some activities might require that other are completed before they can begin
  Activities must be defined so that they meet these criteria and any activities failing to meet these criteria must be redefined

## Slide 5
Project and Activities: Identifying Activities
  Three approaches to identifying activities that makeup a project
    Activity Based Approach
    Product Based Approach
    Hybrid Approach

## Slide 6
    Activity Based Approach
      Consists of creating a list of all activities that the project is thought to involve
      Brainstorming session with the whole project team
      Work Breakdown Structure (WBS) becomes handy

## Slide 7
    Product Based Approach
      Consists of Product Breakdown Structure (PBS) and Product Flow Diagram (PFD)
      PFD indicates for each product which other products are required as inputs

## Slide 8
    Hybrid Approach
      IBM recommended 5 levels in WBS
      Level 1: Project
      Level 2: Deliverables such as software, manuals and training courses
      Level 3: Components which are the key work items needed to produce deliverables such as the modules and tests required to produce the system software
      Level 4: Work packages which are major items or collections of related tasks, required to produce a component
      Level 5: Tasks which are tasks that will normally be the responsibility of a single person

## Slide 9
    Hybrid Approach

## Slide 10
    Sequencing And Scheduling Activities
      Through out a project, schedule is required that clearly indicates when each of the project’s activities is planned to occur and what resources it needs
      Such a plan is presented using a bar chart

## Slide 11
    Network Planning Models
    Critical Path Method (CPM)
    Project Evaluation and Review Technique (PERT)
      Both provides user with project management tools to plan, monitor and update their project as it progresses
    Similarities Between CPM and PERT
      Follow the same steps and use network diagrams
      Used to plan the scheduling of individual activities that make up a project
      Can be used to determine the earliest/latest start and finish times for each activity

## Slide 12
    Differences Between CPM and PERT
      PERT is probabilistic whereas CPM is deterministic
      In CPM, estimates of activity duration are based on historical data
      In PERT, estimates are uncertain and we talk of ranges of duration and the probability that an activity duration will fall into that range
      In routine projects where estimated time for each activity is known, CPM is a better tool to control both time and cost

## Slide 13
    Formulating A Network Model
      Represent the activities and their inter-relationships as graph
    Activity Network Rules and Conventions (Creating Precedence Network)
      A project network should have only one start node and only one end node
      A node has duration
      Links normally have no duration
      Precedents are the immediate preceding activities

## Slide 14
    Activity Network Rules and Conventions (Creating Precedence Network)
      Time moves from left to right
      A network may not contain loops

## Slide 15
    Activity Network Rules and Conventions (Creating Precedence Network)
      A network should not contain dangles

## Slide 16
    Activity Network Rules and Conventions (Creating Precedence Network)
      Representing Lagged Activities

## Slide 17
    Forward Pass Rule
      Earliest start date for an event is the earliest finish date for all the activities terminating at the event
      When more than one activity terminates at a common event, take the latest of the earliest finish dates for those events
    Backward Pass Rule
      Latest date for an event is the latest start date for all the activities that may commence from that event
      When more than one activity commences at a common event, take the earliest of the latest start dates for those events

## Slide 18
    Identifying Critical Path
    Slack Time
      Difference between the earliest date and latest date for an event
      The critical path is the path joining all the nodes with a zero slack

## Slide 19
  Schedule Representation
  Critical Path Method (CPM)

## Slide 21
  Critical Path Method (CPM)

## Slide 22
  PERT Chart (Project Evaluation Review Technique)
    Graphical model that depicts a project’s tasks and relationships between those tasks
    Three time estimates optimistic, most likely, pessimistic

## Slide 23
  PERT Chart (Project Evaluation Review Technique)